## Instructions
Instructions for completing the Project Tasks Matrix
Offerors are required to provide a response, marking the appropriate columns provided in the table below, for each task listed in the tab (10 tabs) included in this workbook. Bidders must provide, for each requirement listed, the corresponding Proposal section reference explaining the Bidder's response. The matrix also provides a column where Bidders may provide additional comments/clarifications related to a specific task response.
Condition | Description
Meets | The Bidder can meet the project task requirement within the parameters of the submitted cost proposal.
Can not meet | The Bidder can not meet the project task requirement within the parameters of the submitted cost proposal.

## Project Management
IV&V Project Management
TASK ITEM | TASK # | TASK DESCRIPTION | MEETS | CAN NOT MEET | BIDDER RESPONSE NARRATIVE SECTION REFERENCE | COMMENTS/CLARIFICATION
IV&V Management Plan | PM-1 | Develop an IV&V Management Plan that describes the activities, personnel, schedule, standards, and methodology for conducting the IV&V reviews for the SHOP Marketplace.
Conduct Initial Review | PM-2 | Prepare and deliver an Initial IV&V report on the required activities. Report on status of each activity.
Conduct Ongoing Review(s) | PM-3 | Prepare and deliver IV&V reports on the required activities.
Management Briefing | PM-4 | Prepare and deliver a formal presentation(s) on the status of the IV&V project. Presented as required.
Project Sponsorship | PM-5 | Assess and recommend improvement, as needed, to assure continuous stakeholder buy-in, participation, support and commitment, and that open pathways of communication exist among all stakeholders.
| PM-6 | Verify that AHIM has bought-in to all changes which impact project objectives, cost, or schedule.
Management Assessment | PM-7 | Verify and assess project management and organization, verify that lines of reporting and responsibility provide adequate technical and managerial oversight of the project.
| PM-8 | Evaluate project progress, resources, budget, schedules, work flow, and reporting.
Project Management | PM-9 | Verify that a Project Management Plan is created and being followed. Evaluate the project management plans and procedures to verify that they are developed, communicated, implemented, monitored and complete.
| PM-10 | Evaluate project reporting plans and actual project reports to verify project status is accurately traced using project metrics.
| PM-11 | Verify that milestones and completion dates are planned, monitored, and met.
| PM-12 | Verify the existence and institutionalization of an appropriate project issue tracking mechanism that documents issues as they arise, enables communication of issues to proper stakeholders, documents a mitigation strategy as appropriate, and tracks the issue to closure. This should include but is not limited to technical and development efforts.
| PM-13 | Evaluate the system’s planned life-cycle development methodology or methodologies (waterfall, evolutionary spiral, rapid prototyping, incremental, etc.) to see if they are appropriate for the system being developed.
Risk Management | PM-14 | Verify that a Project Risk Management Plan is created and being followed.
Change Management | PM-15 | Verify that a Change Management Plan is created and being followed. Evaluate the change management plans and procedures to verify they are developed, communicated, implemented, monitored, and complete, and that resistance to change is anticipated and prepared for. Ensure that the change management plan has standard steps to identify, vet, assess impact, and approve / decline the change via a change control board and appropriate sign-offs.
Communication Management | PM-16 | Verify that a Communication Plan is created and being followed.
Configuration Management | PM-17 | Review and evaluate the configuration management (CM) plans and procedures associated with the development process.
| PM-18 | Verify that all critical development documents, including but not limited to requirements, design, code, rule sets, and configurations maintained under an appropriate level of control.
| PM-19 | Verify that the processes and tools are in place to identify code versions and to rebuild system configurations from source code.
| PM-20 | Verify that appropriate source and object libraries are maintained for training, test, and production and that formal sign-off procedures are in place for approving work products.
| PM-21 | Verify that mechanisms are in place to prevent unauthorized changes being made to the system and to prevent authorized changes from being made to the wrong version.
Project Estimating and Scheduling | PM-22 | Evaluate and make recommendations on the estimating and scheduling process of the project to ensure that the project budget and resources are adequate for the work-breakdown structure and schedule.
| PM-23 | Review schedules to verify that adequate time and resources are assigned for planning, development, review, testing and rework.
Project Personnel | PM-24 | Examine the job assignments, skills, training and experience of the personnel involved in program development.
| PM-25 | Monitor staff turnover and report on the effectiveness of staff replacement policies for both vendors and AHIM staff and the impacts of staff turnover.
Project Organization | PM-26 | Verify that lines of reporting and responsibility provide adequate technical and managerial oversight of the project.
| PM-27 | Verify that the project’s organizational structure supports training, process definition, independent Quality Assurance, Configuration Management, product evaluation, and any other functions critical for the project’s success.
| PM-28 | Verify that the obligations of sub-contractors and external staff (terms, conditions, statement of work, requirements, standards, development milestones, acceptance criteria, delivery dates, etc.), if applicable are clearly defined.
| PM-29 | Verify that the subcontractors’ software development methodology and product standards, if applicable are compatible with the system’s standards and environment.
| PM-30 | Verify that the subcontractor, if applicable has and maintains the required skills, personnel, plans, resources, procedures and standards to meet their commitment. This will include examining the feasibility of any offsite support of the project.
| PM-31 | Verify that any proprietary tools used by subcontractors, if applicable do not restrict the future maintainability, portability, and reusability of the system.
AHIM Oversight | PM-32 | Verify that AHIM oversight is provided in the form of periodic status reviews and technical interchanges.
| PM-33 | Verify that AHIM has defined the technical and managerial inputs the subcontractor(s), if applicable need (reviews, approvals, requirements and interface clarifications, etc.) and has the resources to supply them on schedule.
| PM-34 | Verify that AHIM staff has the ultimate responsibility for monitoring project cost and schedule.

## Quality Management
Quality Management
TASK ITEM | TASK # | TASK DESCRIPTION | MEETS | CAN NOT MEET | BIDDER RESPONSE NARRATIVE SECTION REFERENCE | COMMENTS/CLARIFICATION
Quality Assurance | QA-1 | Evaluate and make recommendations on the project’s Quality Assurance plans, procedures and organization.
| QA-2 | Verify that the QA function has an appropriate level of independence from project management.
| QA-3 | Verify that the QA function monitors the fidelity of all defined processes in all phases of the project.
| QA-4 | Verify that the quality of all products produced by the project is monitored by formal reviews and sign-offs.
| QA-5 | Verify that project self-evaluations are performed and that measures are continually taken to improve the process.
| QA-6 | Monitor the performance of the QA function by reviewing its processes and reports and performing spot checks of system documentation; assess findings and performance of the processes and reports.
| QA-7 | Verify that QA has an appropriate level of independence; evaluate and make recommendations on the project’s Quality Assurance plans, procedures and organization.
| QA-8 | Evaluate if appropriate mechanisms are in place for project self-evaluation and process improvement.
Process Definition and Product Standards | QA-9 | Review and make recommendations on all defined processes and product standards associated with the system development.
| QA-10 | Verify that all major development processes are defined and that the defined and approved processes and standards are followed in development.
| QA-11 | Verify that the processes and standards are compatible with each other and with the system development methodology.
| QA-12 | Verify that all process definitions and standards are complete, clear, up-to-date, consistent in format, and easily available to project personnel.

## Training
Training
TASK ITEM | TASK # | TASK DESCRIPTION | MEETS | CAN NOT MEET | BIDDER RESPONSE NARRATIVE SECTION REFERENCE | COMMENTS/CLARIFICATION
User Training and Documentation | TR-1 | Review and make recommendations on the training provided to system users. Verify sufficient knowledge transfer for maintenance and operation of the new system.
| TR-2 | Verify that training for users is instructor-led and hands-on and is directly related to the business process and required job skills.
| TR-3 | Verify that user-friendly training materials and help desk services are easily available to all users.
| TR-4 | Verify that all necessary policy and process and documentation is easily available to users.
| TR-5 | Verify that all training is given on-time and is evaluated and monitored for effectiveness, with additional training provided as needed.
Developer Training and Documentation | TR-6 | Review and make recommendations on the training provided to system developers.
| TR-7 | Verify that developer training is technically adequate, appropriate for the development phase, and available at appropriate times.
| TR-8 | Verify that all necessary policy, process and standards documentation is easily available to developers.
| TR-9 | Verify that all training is given on-time and is evaluated and monitored for effectiveness, with additional training provided as needed.

## Requirements Management
Requirements Management
TASK ITEM | TASK # | TASK DESCRIPTION | MEETS | CAN NOT MEET | BIDDER RESPONSE NARRATIVE SECTION REFERENCE | COMMENTS/CLARIFICATION
Requirements Management | RM-1 | Evaluate and make recommendations on the project’s process and procedures for managing system and software requirements.
| RM-2 | Verify that system requirements are well-defined, understood and documented.
| RM-3 | Evaluate the allocation of system requirements to hardware and software requirements.
| RM-4 | Verify that software requirements can be traced through design, code and test phases to verify that the system performs as intended and contains no unnecessary software elements.
| RM-5 | Verify that requirements are under formal configuration control.
Security Requirements | RM-6 | Evaluate and make recommendations on project policies and procedures for ensuring that the system is secure and that the privacy of client data is maintained.
| RM-7 | Evaluate the projects restrictions on system and data access.
| RM-8 | Evaluate the projects security and risk analysis.
| RM-9 | Verify that processes and equipment are in place to back up client and project data and files and archive them safely at appropriate intervals.
Requirements Analysis | RM-10 | Verify that an analysis of AHIM and federal needs and objectives has been performed to verify that requirements of the system are well understood, well defined, and satisfy federal regulations.
| RM-11 | Verify that all stakeholders have been consulted to the desired functionality of the system, and that users have been involved in prototyping of the user interface.
| RM-12 | Verify that all stakeholders have bought-in to all changes which impact project objectives, cost, or schedule.
| RM-13 | Verify that performance requirements (e.g. timing, response time and throughput) satisfy user needs
| RM-14 | Verify that user’s maintenance requirements for the system are completely specified
Interface Requirements | RM-15 | Verify that all system interfaces are exactly described, by medium and by function, including input/output control codes, data format, polarity, range, units, and frequency.
| RM-16 | Verify that approved interface documents are available and that appropriate relationships (such as interface working groups) are in place with all agencies and organizations supporting the interfaces.
Requirements Allocation and Specification | RM-17 | Verify that all system requirements have been allocated to either a software or hardware subsystem.
| RM-18 | Verify that requirements specifications have been developed for all hardware and software subsystems in a sufficient level of detail to ensure successful implementation.
Reverse Engineering | RM-19 | If a legacy system or a transfer system is or will be used in development, Verify that a well-defined plan and process for reengineering the system is in place and is followed. The process, depending on the goals of the reuse/transfer, may include reverse engineering, code translation, re-documentation, restructuring, normalization, and re-targeting.

## Operating Environment
Operating Environment
TASK ITEM | TASK # | TASK DESCRIPTION | MEETS | CAN NOT MEET | BIDDER RESPONSE NARRATIVE SECTION REFERENCE | COMMENTS/CLARIFICATION
System Hardware | OE-1 | Evaluate new and existing system hardware configurations to determine if their performance is adequate to meet existing and proposed system requirements
| OE-2 | Determine if hardware is compatible with AHIM’s and the State’s (as necessary) existing processing environment, if it is maintainable, and if it is easily upgradeable. This evaluation will include, but is not limited to CPUs and other processors, memory, network connections and bandwidth, communication controllers, telecommunications systems (LAN/WAN), terminals, printers and storage devices.
| OE-3 | Evaluate current and projected vendor support of the hardware, as well as the AHIM’s hardware configuration management plans and procedures.
System Software | OE-4 | Evaluate new and existing system software to determine if its capabilities are adequate to meet existing and proposed system requirements.
| OE-5 | Determine if the software is compatible with AHIM’s existing hardware and software environment (as needed), if it is maintainable, and if it is easily upgradeable. This evaluation will include, but is not limited to, operating systems, middleware, and network software including communications and file-sharing protocols.
| OE-6 | Current and projected vendor support of the software will also be evaluated, as well as the AHIM’s software acquisition plans and procedures.
Database Software | OE-7 | Evaluate new and existing database products to determine if their capabilities are adequate to meet existing and proposed system requirements.
| OE-8 | Determine if the database’s data format is easily convertible to other formats, if it supports the addition of new data items, if it is scalable, if it is easily refreshable and if it is compatible with the AHIM’s existing hardware and software, including any on-line transaction processing (OLTP) environment.
| OE-9 | Evaluate any current and projected vendor support of the software, as well as the AHIM’s software acquisition plans and procedures.
System Capacity | OE-10 | Evaluate the existing processing capacity of the system and verify that it is adequate for current statewide needs for both batch and on-line processing.
| OE-11 | Evaluate the historic availability and reliability of the system including the frequency and criticality of system failure.
| OE-12 | Evaluate the results of any volume testing or stress testing.
| OE-13 | Evaluate any existing measurement and capacity planning program and will evaluate the system’s capacity to support future growth.
| OE-14 | Make recommendations on changes in processing hardware, storage, network systems, operating systems, COTS software, and software design to meet future growth and improve system performance.

## Development Environment
Development Environment
TASK ITEM | TASK # | TASK DESCRIPTION | MEETS | CAN NOT MEET | BIDDER RESPONSE NARRATIVE SECTION REFERENCE | COMMENTS/CLARIFICATION
Development Hardware | DE-1 | Evaluate new and existing development hardware configurations to determine if their performance is adequate to meet the needs of system development.
| DE-2 | Determine if hardware is maintainable, easily upgradeable, and compatible with the AHIM’s existing development and processing environment. This evaluation will include, but is not limited to CPUs and other processors, memory, network connections and bandwidth, communication controllers, telecommunications systems (LAN/WAN), terminals, printers and storage devices.
| DE-3 | Current and projected vendor support of the hardware will also be evaluated, as well as the AHIM’s hardware configuration management plans and procedures.
Development Software | DE-4 | Evaluate new and existing development software to determine if its capabilities are adequate to meet system development requirements.
| DE-5 | Determine if the software is maintainable, easily upgradeable, and compatible with the AHIM’s existing hardware and software environment.
| DE-6 | Evaluate the environment as a whole to see if it shows a degree of integration compatible with good development. This evaluation will include, but is not limited to, operating systems, network software, CASE tools, project management software, configuration management software, compilers, cross-compilers, linkers, loaders, debuggers, editors, and reporting software.
| DE-7 | Language and compiler selection will be evaluated with regard to portability and reusability (ANSI standard language, non-standard extensions, etc.)
| DE-8 | Current and projected vendor support of the software will also be evaluated, as well as the States software acquisition plans and procedures.

## Software Development
Software Development
TASK ITEM | TASK # | TASK DESCRIPTION | MEETS | CAN NOT MEET | BIDDER RESPONSE NARRATIVE SECTION REFERENCE | COMMENTS/CLARIFICATION
High-Level Design | SD-1 | Evaluate and make recommendations on existing high level design products to verify the design is workable, efficient, and satisfies all system and system interface requirements.
| SD-2 | Evaluate the design products for adherence to the project design methodology and standards.
| SD-3 | Evaluate the design and analysis process used to develop the design and make recommendations for improvements. Evaluate design standards, methodology and CASE tools, if applicable used will be evaluated and make recommendations.
| SD-4 | Verify that design requirements can be traced back to system requirements.
| SD-5 | Verify that all design products are under configuration control and formally approved before detailed design begins.
Detailed Design | SD-6 | Evaluate and make recommendations on existing detailed design products to verify that the design is workable, efficient, and satisfies all high level design requirements.
| SD-7 | The design products will also be evaluated for adherence to the project design methodology and standards.
| SD-8 | The design and analysis process used to develop the design will be evaluated and recommendations for improvements made.
| SD-9 | Design standards, methodology and CASE tools, if applicable, used will be evaluated and recommendations made.
| SD-10 | Verify that design requirements can be traced back to system requirements and high level design.
| SD-11 | Verify that all design products are under configuration control and formally approved before coding begins.
Job Control | SD-12 | Perform an evaluation and make recommendations on existing job control and on the process for designing job control.
| SD-13 | Evaluate the system’s division between batch and on-line processing with regard to system performance and data integrity.
| SD-14 | Evaluate batch jobs for appropriate scheduling, timing and internal and external dependencies.
| SD-15 | Evaluate the appropriate use of OS scheduling software.
| SD-16 | Verify that job control language scripts are under an appropriate level of configuration control.
Code | SD-17 | Evaluate and make recommendations on the standards and process currently in place for code development.
| SD-18 | Evaluate the existing code base for portability and maintainability, taking software metrics including but not limited to modularity, complexity and source and object size.
| SD-19 | Code documentation will be evaluated for quality, completeness (including maintenance history) and accessibility.
| SD-20 | Evaluate the coding standards and guidelines and the projects compliance with these standards and guidelines. This evaluation will include, but is not limited to, structure, documentation, modularity, naming conventions and format.
| SD-21 | Verify that developed code is kept under appropriate configuration control and is easily accessible by developers.
| SD-22 | Evaluate the project’s use of software metrics in management and quality assurance.
| SD-23 | Evaluate custom and COTS software for the ability to manage business rules and user workflows through end-user configurable tools verses coding changes
Configuration and Rules | SD-24 | Evaluate the process for updating rule sets and configurations in a sustainable and auditable manner
| SD-25 | Evaluate the overall plan for maintaining product configurations and rules. Evaluate the framework used for categorizing HIX work products into various categories of reuse by other states inclusive of clear pre-requisites for re-usable components (e.g. purchase of COTS software licenses, similar underlying technology stack, etc.)
Reuse and Shared Services | SD-26 | Evaluate the process for developing agreements with other States in reusing software components.
| SD-27 | Evaluate the implementation of shared services with other States.
Unit Test | SD-28 | Evaluate the plans, requirements, environment, tools, and procedures used for unit testing system modules.
| SD-29 | Evaluate the level of test automation, interactive testing and interactive debugging available in the test environment.
| SD-30 | Verify that an appropriate level of test coverage is achieved by the test process, that test results are verified, that the correct code configuration has been tested, and that the tests are appropriately documented.

## System and Acceptance Testing
System And Acceptance Testing
TASK ITEM | TASK # | TASK DESCRIPTION | MEETS | CAN NOT MEET | BIDDER RESPONSE NARRATIVE SECTION REFERENCE | COMMENTS/CLARIFICATION
System Integration Test | ST-1 | Evaluate the plans, requirements, environment, tools, and procedures used for integration testing of system modules.
| ST-2 | Evaluate the level of automation and the availability of the system test environment.
| ST-3 | Verify that an appropriate level of test coverage is achieved by the test process, that test results are verified, that the correct code configuration has been tested, and that the tests are appropriately documented, including formal logging of errors found in testing.
| ST-4 | Verify that the test organization has an appropriate level of independence from the development organization.
Interface Testing | ST-10 | Evaluate interface testing plans and procedures for compliance with industry standards.
Acceptance and Turnover | ST-11 | Acceptance procedures and acceptance criteria for each product must be defined, reviewed, and approved prior to test and the results of the test must be documented. Acceptance procedures must also address the process by which any software product that does not pass acceptance testing will be corrected.
| ST-12 | Verify that appropriate acceptance testing based on the defined acceptance criteria is performed satisfactorily before acceptance of software products.
| ST-13 | Verify that the acceptance test organization has an appropriate level of independence from the contractor.
| ST-14 | Verify that training in using the contractor-supplied software is be on-going throughout the development process, especially if the software is to be turned over to State staff for operation.
| ST-15 | Review and evaluate implementation plan.

## Data Management
Data Management
TASK ITEM | TASK # | TASK DESCRIPTION | MEETS | CAN NOT MEET | BIDDER RESPONSE NARRATIVE SECTION REFERENCE | COMMENTS/CLARIFICATION
Data Conversion | DM-1 | Evaluate AHIM’s existing and proposed plans, procedures and software for data conversion.
| DM-2 | Verify that procedures are in place and are being followed to review the completed data for completeness and accuracy and to perform data clean-up as required.
| DM-3 | Determine conversion error rates and if the error rates are manageable.
| DM-4 | Make recommendations on making the conversion process more efficient and on maintaining the integrity of data during the conversion.
Database Design | DM-5 | Evaluate new and existing database designs to determine if they meet existing and proposed system requirements.
| DM-6 | Recommend improvements to existing designs to improve data integrity and system performance.
| DM-7 | Evaluate the design for maintainability, scalability, refreshability, concurrence, normalization (where appropriate) and any other factors affecting performance and data integrity.
| DM-8 | Evaluate the project’s process for administering the database, including backup, recovery, performance analysis and control of data item creation.

## Operations and Management
Operations and Maintenance
TASK ITEM | TASK # | TASK DESCRIPTION | MEETS | CAN NOT MEET | BIDDER RESPONSE NARRATIVE SECTION REFERENCE | COMMENTS/CLARIFICATION
Systems Operations | OM-1 | Evaluate AHIM’s existing and proposed plans and procedures for systems operations and performance monitoring.
| OM-2 | Verify that procedures are in place and are being followed to track performance metrics according to established systems service level agreements.
| OM-3 | Verify that procedures are in place for systems monitoring, security, back-up, and recovery including disaster recovery and business continuity.
| OM-4 | Determine whether system administration roles and responsibilities are clearly defined and staff levels are adequate to perform systems operations and achieve operational service levels.
| OM-5 | Make recommendations on bolstering systems maintenance procedures to ensure that service levels are met.
Systems Maintenance | OM-6 | Evaluate the State’s existing and proposed plans, procedures and software for systems maintenance
| OM-7 | Verify that procedures are in place and are being followed to manage issues, defects, and risks from initial capture through resolution and disposition
| OM-8 | Determine whether system maintenance roles and responsibilities are clearly defined and staff levels are adequate to achieve maintenance activities
| OM-9 | Verify that the software maintenance agreements are in place with the COTS vendors and that the support provided by those vendors conforms to licensing and software maintenance agreements and are adequate to support Arkansas' software maintenance needs
| OM-10 | Make recommendations on optimizing systems maintenance activities ensuring that performance targets are met and risks to operations are minimized
Systems Enhancements/ Upgrades | OM-11 | Evaluate the Vendor’s existing and proposed plans for applying the latest COTS products and releases to AHIM
| OM-12 | Verify that the Vendor has adequate technical environments in place to support development, testing, production staging, production operations, etc. as well as adequate processes and procedures to manage those environments
| OM-13 | Determine whether systems enhancements and upgrades roles and responsibilities are clearly defined and that staff levels or the ability to bring in as-needed contract support are adequate to perform necessary software enhancements and upgrades with minimum business operations disruption
| OM-14 | Make recommendations on optimizing the process for applying systems enhancements and upgrades to minimize risk to business operations